## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| system for automating and managing the Um al-Zanar Center for Relief and Development | christen sa | 2020-06-01 | 2020-06-22 |  | 30% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Buliding interface | Design | christen sa | 2 | 2020-06-01 | 2020-06-10 | 9 | Complete
| Contatct the customer for the details |  | christen sa |  | 2020-06-01 | 2020-06-05 | 4 | Complete
| Interface design |  | reem sa |  | 2020-06-05 | 2020-06-08 | 3 | Complete
| Error Review |  | qamar sa |  | 2020-06-08 | 2020-06-10 | 2 | Complete
| DataBase |  | qamar sa | 1 | 2020-06-12 | 2020-06-16 | 4 | In Progress
| Erd Design |  | qamar sa |  | 2020-06-12 | 2020-06-13 | 1 | In Progress
| Tables design |  | christen sa |  | 2020-06-13 | 2020-06-15 | 2 | In Progress
| Data Entry |  | reem sa |  | 2020-06-15 | 2020-06-16 | 1 | Not Started
| Achieve program contact with the Database |  | reem sa |  | 2020-06-16 | 2020-06-22 | 6 | Not Started
| Building a network between Device |  | reem sa |  | 2020-06-16 | 2020-06-18 | 2 | Not Started
| Connect the Program |  | qamar sa |  | 2020-06-18 | 2020-06-19 | 1 | Not Started
| The final Test |  | christen sa |  | 2020-06-19 | 2020-06-22 | 3 | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.